## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Subject | Description | Status ID | Status | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3641380 | 68329 | ATM Project | 3 | ATM_1-3 | 292628 | Bug | 92423 | Exploratory Testing | Account 2 balance inquiry | Account 2 shoudn't have the option of a Savings account as it doesn't have that account according to the manual. (Version 1.1) Not solved | 2 | In Progress |  |  | 319804 | Jay Gurjar | 319804 | Jay Gurjar | Jan. 23, 2022 11:53 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:56 | 0 | 0
3641377 | 68329 | ATM Project | 1 | ATM_1-1 | 292628 | Bug | 92423 | Exploratory Testing | Money market Bug | Money market bug found with account number 1 and pin 42. It didn't print $5000 as said in the manual. This shouldn't even show the option of money market as the manual says Money market is not allowed for Pin 42 and Card no: 1. (Version 1.1) Error resolved | 3 | Resolved |  |  | 319804 | Jay Gurjar | 319804 | Jay Gurjar | Jan. 23, 2022 11:35 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:54 | 0 | 0
3641379 | 68329 | ATM Project | 2 | ATM_1-2 | 292628 | Bug | 92423 | Exploratory Testing | Money Market Testing Crash | Tried to perform another transaction after the initial bug of not being displayed $5000, tried to display balance in Money Market again. The code crashed and the screen went all green, with no transaction details even in the log file. This shouldn't even show the option of money market as the manual says Money market is not allowed for Pin 42 and Card no: 1. (Version 1.1) Error not solved. | 2 | In Progress |  |  | 319805 | Ali Siddiqi | 319804 | Jay Gurjar | Jan. 23, 2022 11:46 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:52 | 0 | 0
3641385 | 68329 | ATM Project | 4 | ATM_1-4 | 292628 | Bug | 92423 | Exploratory Testing | Off button | The off button does not work after you perform multiple transactions. This is annoying. (Version 1.1) Off button isn't working | 2 | In Progress |  |  | 319805 | Ali Siddiqi | 319804 | Jay Gurjar | Jan. 23, 2022 12:03 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:50 | 0 | 0
3645504 | 68329 | ATM Project | 19 | ATM_1-19 | 292628 | Bug | 92423 | Exploratory Testing | Withdrawing from Account 2 | Tried withdrawing $60, instead, the system withdrew $100. (Version 1.1) Error resolved. | 3 | Resolved |  |  |  |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:49 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:49 | 0 | 0
3641398 | 68329 | ATM Project | 6 | ATM_1-6 | 292628 | Bug | 92423 | Exploratory Testing | Withdrawal bug | Account 2: Tried withdrawing $100 from the chequing account after having 100 $20 bills in the initial stage. It didn't allow us to withdraw 100$ which was selected. (Version 1.1) Error solved | 3 | Resolved |  |  | 319802 | LAB1-18 | 319804 | Jay Gurjar | Jan. 23, 2022 12:16 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:46 | 0 | 0
3641503 | 68329 | ATM Project | 12 | ATM_1-12 | 292628 | Bug | 92423 | Exploratory Testing | Exploratory - Take Receipt Button Testing | When the "take receipt" button is pressed the screen goes blank and no further action is performed in receiving of receipt. (Version 1.1) The white screen goes blank but the system still takes input. | 2 | In Progress |  |  | 319802 | LAB1-18 | 319802 | LAB1-18 | Jan. 23, 2022 16:29 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:43 | 0 | 0
3641506 | 68329 | ATM Project | 13 | ATM_1-13 | 292628 | Bug | 92423 | Exploratory Testing | Exploratory - Card Number 2 cannot access Money Market inquiry | Account Number - 2 PIN - 1234 Balance inquiry for this account for Money Market displays Invalid account type. (Version 1.1) Error Resolved | 3 | Resolved |  |  | 319802 | LAB1-18 | 319802 | LAB1-18 | Jan. 23, 2022 16:37 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:41 | 0 | 0
3641510 | 68329 | ATM Project | 15 | ATM_1-15 | 292628 | Bug | 92423 | Exploratory Testing | Exploratory - Withdrawal Error | Account Number - 2 PIN - 1234 Account contains 1000$ ATM does not permit withdrawal of 20$ Prompt - Insufficient cash available. (Version 1.1) Gives invalid account error | 2 | In Progress |  |  | 319802 | LAB1-18 | 319802 | LAB1-18 | Jan. 23, 2022 16:44 |  | 319804 | Jay Gurjar | Jan. 24, 2022 19:39 | 0 | 0
3641515 | 68329 | ATM Project | 16 | ATM_1-16 | 292628 | Bug | 92423 | Exploratory Testing | Exploratory - Incorrect option from list | when an incorrect option is selected from the menu for example by clicking 6, it displayed the amount from the previous transaction ![image][pasted-2022.01.23-16.56.46.png] | 3 | Resolved | 0 | Fixed | 319802 | LAB1-18 | 319802 | LAB1-18 | Jan. 23, 2022 16:57 |  | 319802 | LAB1-18 | Jan. 23, 2022 17:28 | 1 | 0 | Jan. 23, 2022 16:58 LAB1-18 Issue fixed in version 1.1 | Jan. 23, 2022 17:28 LAB1-18 Issue fixed in Version 1.1
3641517 | 68329 | ATM Project | 17 | ATM_1-17 | 292628 | Bug | 92423 | Exploratory Testing | Exploratory - Transfer Error | Account Number - 2 PIN - 1234 When attempting to Transfer from Money Market to Checking. ATM performs transfer from Checking to Money market. This is the opposite of what is requested by the client. | 2 | In Progress |  |  | 319802 | LAB1-18 | 319802 | LAB1-18 | Jan. 23, 2022 17:04 |  | 319802 | LAB1-18 | Jan. 23, 2022 17:19 | 1 | 0 | Jan. 23, 2022 17:19 LAB1-18 Defect still exists in version 1.1. Balance transferred is correct, its just that the receipt displays incorrect transfer. ![image][pasted-2022.01.23-17.18.37.png]
3641395 | 68329 | ATM Project | 5 | ATM_1-5 | 292628 | Bug | 92423 | Exploratory Testing | Money Market Bug 2.0 | The money market is not available on Card no: 2 and Pin: 1234 which should be theoretically available from the document. | 3 | Resolved | 0 | Fixed | 319803 | Mohamed Numan` | 319804 | Jay Gurjar | Jan. 23, 2022 12:07 |  | 319802 | LAB1-18 | Jan. 23, 2022 17:14 | 1 | 0 | Jan. 23, 2022 17:14 LAB1-18 Issue fixed in version 1.1. Using account number 2 the correct $5000 was displayed. ![image][pasted-2022.01.23-17.14.45.png]